## Task List
Week of May 18 thru May 24 (DATES PASSED/ TASKS COMPLETE)
Interactive Study Tasks | DUE DATE FREQUENCY | Monday 5/18 | Tuesday 5/19 | Wednesday 5/20 | Thursday 5/21 | Friday 5/22- 5/24
E-mail Updates on Progress | Bi-Weekly |  | Entire Team Update |  | Entire Team Update
Zero Feature Release/ Application Development | Bi-Weekly | Chris/Rob- Complete the main page to include buttons for a resource page, topic list, subtopic list; create pages for resources, topics, quizzes |  | Rob/Chris - Due by Friday: Link the buttons for quizes to the appropriate pages, enter a test question, write the code to review the answer and give user feedback
Question Input | Bi-Weekly | Niki- Complete Lifecycle Models Question input on the Google Doc |  | Bonnie- Complete the Life Cycle Architecture question section in the Google Doc |  | Kalee- Complete the UML diagrams question section in the Google Doc
Integrating the Questions | Bi-Weekly |  | Kalee- Integrate the Lifecycle Models Questions into the application in the correct quiz page |  | Niki- Integrate the Life Cycle Achitecture Questions into the application in the correct quiz page | Bonnie- Integrate the UML diagrams Questions into the application in the correct quiz page
Testing Main Page | Bi-Weekly |  | Marc- Recieve access to the initial code from Chris/Rob via the Google Doc, test all of the buttons | Marc- Test the integration of the Lifecycle Models Questions |  | Marc- Test the integration of the Life Cycle Architecture Questions and UML diagram Questions
Documentation Updates | Bi- Weekly | Kalee- Complete updated Task Lists |  |  | Rob/Chris- Complete the Class Diagram | Marc/Bonnie/Niki- Complete multiple Use Cases to include in Requirements Document
Week of May 25 thru May 31 (DATES PASSED/ TASKS COMPLETE)
Interactive Study Tasks | DUE DATE FREQUENCY | Monday 5/25 | Tuesday 5/26 | Wednesday 5/27 | Thursday 5/28 | Friday 5/29- 5/31
E-mail Updates on Progress | Bi-Weekly |  | Entire Team Update |  | Entire Team Update
Application Development | Bi-Weekly | Chris/Rob- Add additional pages for new topics and subtopics |  | Rob/Chris - Make interactive buttons for the additional pages created | Beta Release
Question Input | Bi-Weekly | Niki- Complete the Resource List |  | Bonnie- Complete the questions on Use Cases | Beta Release | Kalee- Complete the UML diagrams question section in the Google Doc
Integrating the Questions | Bi-Weekly |  | Kalee- Integrate the Resource List into the Resources page in the application |  | Niki- Integrate the questions on Use Cases into the appropriate page | Bonnie- Integrate the UML diagrams Questions into the application in the correct quiz page
Testing Main Page | Bi-Weekly |  | Marc- Test all of the functionality of the questions and answers input so far. Make sure the correct solutions are provided, be sure the Resource Page is correct | Marc- Test the integration of the Resource list | Beta Release | Marc- Test the integration of the Use Cases questions
Documentation Updates | Bi- Weekly | Kalee- Add an introduction into Requirements Documentation |  |  | Team- Read through the updated documentation and provide feedback
Week of June 1 thru June 6
Interactive Study Tasks | DUE DATE FREQUENCY | Monday 6/1 | Tuesday 6/2 | Wednesday 6/3 | Thursday 6/4 | Friday 6/5
E-mail Updates on Progress | Bi-Weekly |  | Entire Team Update |  | Entire Team Update
Application Development | Bi-Weekly | Chris/Rob- Work on applications asthetics |  |  | Presentation | Development Complete- Final Release
Question Input | Bi-Weekly | Niki/ Kalee/Bonnie- Fill in questions and answers |  |  | Presentation | Question Input Complete- Final Release
Integrating the Questions | Bi-Weekly |  | Kalee/Niki/Bonnie- Integrate any last minute questions to the appropriate pages |  | Presentation | Integration Complete- Final Release
Testing Main Page | Bi-Weekly | Team- Test, Test, Test | Team- Test, Test, Test | Team- Test, Test, Test | Presentation | Testing Complete- Final Release
Documentation Updates | Bi- Weekly | Documentation is Complete | Kalee- Create powerpoint for presentation | Documentation is Complete | Documentation is Complete | Documentation Complete- Final Release